## Sheet1
NAME | DATE | MINUTES | COMMIT | NOTES
Kay | 2020-07-14 | 360 | https://github.com/chat-loc/chatloc.github.io/commit/5b453f6698e6f71651e4867989b178d7997049c7 | Design Registration module and introduce project theme
Kay | 2020-07-14 | 60 | https://github.com/chat-loc/chatloc.github.io/commit/8d6ef75e89a64a98c585ce4a538bb63216b75358 | Set up Express server
Kay | 2020-07-14 | 60 | https://github.com/chat-loc/chatloc.github.io/commit/8d6ef75e89a64a98c585ce4a538bb63216b75358 | Set up Controllers and Express-handlebars
Kay | 2020-07-15 | 80 | https://github.com/chat-loc/chatloc.github.io/commit/45c76a95645be3bca0cea6a7b01ed817519e2d2e | Set up User Model, MongoDB connection (Atlas)
Kay | 2020-07-20 | 40 | https://github.com/chat-loc/chatloc.github.io/commit/5adae418b3a45a7a720cd2cf1a1f18654c61702f | Create Login module
Kay | 2020-07-21 | 200 | https://github.com/chat-loc/chatloc.github.io/commit/20e1f9174e1e0fe7a9632a09e14cce2207b1dbb9 | Implement validation on login and reg modules
Kay | 2020-07-23 | 400 | https://github.com/chat-loc/chatloc.github.io/commit/0875225b922b75c89b5a27c6aaa299c8d0848906 | Implement session auth to all pages, connect to Opencage and Mapbox API
Kay | 2020-07-23 | 85 | https://github.com/chat-loc/chatloc.github.io/commit/8b7b4939abb291100c7f578a28b303f3175f105a | List room user can join based on location and origin
Kay | 2020-07-24 | 400 | https://github.com/chat-loc/chatloc.github.io/commit/acb93abf9822dec4fbcaf40b47b29ccba141609b | Build working prototype
Kay | 2020-07-16 |  | https://github.com/chat-loc/chatloc.github.io/commit/a163e7993922b9cb53cd31d23468ec79c11d9f12 | Convert app to React
Kay | 2020-07-16 |  | https://github.com/chat-loc/chatloc.github.io/commit/ddc5dea7fdecb8e285a2ddf5530b229f41736e5d | Convert app to React II (Heroku MERN Deployment Reconfig)
Khushboo | 2020-07-11 | 450 | https://github.com/chat-loc/chatloc.github.io/pull/26/commits/3398a9cf0b0f7920890fe363bfc6e728045f48c7 | Created landing page, css files and login page
Khushboo / Aman | 2020-07-20 | 400 | https://github.com/chat-loc/chatloc.github.io/commit/a28fef4d8582293946dbff07fa83c1827432158f | Creating chat user interface
Khushboo / Aman | 2020-07-02 | 390 | https://github.com/chat-loc/chatloc.github.io/commit/a45398dcb5d9e7db44ce3e49223b552742ae46c3 | Making login logout and room list responsive with Aman
Khushboo / Aman | 2020-08-07 | 250 | https://github.com/chat-loc/chatloc.github.io/commit/286ca9c3a8555e0c7234327dfac620043f4d2921 | dark mode theme with Aman
Khushboo / Aman | 2020-08-08 | 10 | https://github.com/chat-loc/chatloc.github.io/commit/fa82cd20851166d39e7316799dab1363fe4a4404 | merging the dark mode theme to master branch with Aman
Aman | 2020-07-14 | 60 |  | Meeting with group members regarding the functionality of the project.
Aman | 2020-07-19 | 120 | https://github.com/chat-loc/chatloc.github.io/commit/c6f69a87d1698e04e60acdd479490a2a3242d193 | Integrated news api for chat suggestion feature issue #10. Waiting for chat module for display of the feature.
Aman / Khushboo | 2020-07-23 | 180 | https://github.com/chat-loc/chatloc.github.io/pull/26/commits/3398a9cf0b0f7920890fe363bfc6e728045f48c7 | Helped Khushboo with responsiveness of the website.
Aman / Khushboo | 2020-07-24 | 180 | https://github.com/chat-loc/chatloc.github.io/commit/a28fef4d8582293946dbff07fa83c1827432158f | Working on the Chat functionality.
Aman / Khushboo | 2020-07-05 | 200 | https://github.com/amnsworld/chatapp-react | React conversion- Login page, register module, chatroom module
Aman / Khushboo | 2020-07-06 | 150 | https://github.com/amnsworld/chatapp-react | React conversion- roomlist module
Aman / Khushboo | 2020-07-06 | 120 | https://github.com/amnsworld/chatapp-react | React conversion- not found module,